Scope Change Register

ReMarkets — Bid Intelligence Platform

Option B — Blazor Web App + .NET 10

This document tracks all scope changes to the estimation driven by client Q&A answers, stakeholder feedback, and discovery findings. Each change is linked to the specific client response that triggered it.

# Baseline Estimation

Baseline is post-SC-002 estimation. See SC_002/scope-changes.json for previous changes.

| Metric | Value |
| --- | --- |
| Baseline Date | 2026-02-26 |
| MVP Hours (Auth Option A) | ~998 hrs |
| Post-MVP Hours | ~117 hrs |
| Learning Curve | ~56 hrs |
| Full Scope (MVP + Post-MVP + Learning) | ~1171 hrs |

# SC-003: Client Q&A — Answers A17–A18 (critical questions Q28 and Q14)

Date: 2026-03-03    |    2 changes    |    Net impact: 0 hrs

CONFIRMED  A17 — Inventory in Multiple Active Offers Simultaneously (Q28)

Client answer: "Yes — the same inventory line can appear in multiple active offers at the same time. Bid validation still enforces qty <= current available at time of entry. Inventory is only committed at allocation approval, not at bid entry. The system should not reserve inventory at the bid stage. At allocation approval: system must display current available quantity; if allocations exceed available, system warns Admin; Admin adjusts and makes final decision."

Change: This confirms the system's existing design — there was never a one-offer-per-inventory-line lock. The estimation already models: (1) strict bid validation at entry checking real-time available qty (A12/SC-002, covered in #19), (2) inventory commitment only at approval (#28, 18 hrs), (3) approval workflow where Admin reviews and decides (#26, 48 hrs), (4) Admin override capability (#25, 18 hrs). The 'warn if exceeds available' behavior is standard approval validation — you cannot commit inventory without checking it exists. No new scope required.

Estimation items affected:

- #19 MudBlazor DataGrid — in-cell editing (56 hrs) — bid validation at entry already included

- #25 Admin override of winning customer (18 hrs) — Admin decision authority already included

- #26 Approval workflow (48 hrs) — availability check at approval is inherent to committing inventory

- #28 Automatic inventory commitment on approval (18 hrs) — commit logic must verify available qty

| Hours Added | Hours Removed | Net Impact |
| --- | --- | --- |
| — | — | 0 hrs |

CONFIRMED  A18 — Unallocated Quantity After Partial Allocation: Auto-Release (Q14)

Client answer: "Option A — Auto-release. After partial allocation: allocated quantity moves to Committed, remaining quantity returns to Available inventory. Original bid marked 'Partially Allocated.' Remaining quantity is not reserved — can be bid on again, allocated to other customers, included in future offers. No special 'pending hold' logic in Phase 1."

Change: Client chose the simplest of the three options we proposed (auto-release, hold pending, admin decides). This is the natural behavior of the system as already designed: when you commit 60 of 100, the 40 were never committed — they remain Available by definition. The 'Partially Allocated' bid status is a derived state within the existing split allocation scope (#34, 48 hrs) — if allocated_qty < bid_qty, the bid is partially allocated. No new entities, states, or workflows required.

Estimation items affected:

- #34 Partial/split allocations across customers (48 hrs) — partial allocation status is a derived state within this item

- #16 State transitions — automatic on approval + manual override (24 hrs) — Available/Committed transitions already modeled

- #28 Automatic inventory commitment on approval (18 hrs) — commits only allocated qty, remainder stays Available

| Hours Added | Hours Removed | Net Impact |
| --- | --- | --- |
| — | — | 0 hrs |

## Batch Summary

| Metric | Before | After |
| --- | --- | --- |
| MVP Hours (Auth Option A) | ~998 hrs | ~998 hrs |
| Full Scope (MVP + Post-MVP + Learning) | ~1171 hrs | ~1171 hrs |
| Total Hours Added |  | +0 hrs |
| Total Hours Removed |  | -0 hrs |
| Net Impact on MVP |  | 0 hrs |
| MVP Timeline (2 devs) |  | ~3.3 months (~13.2 wks) |
| Full Scope (2 devs) |  | ~3.7 months (~14.6 wks) |
| MVP Timeline (3 devs) |  | ~2.2 months (~8.8 wks) |
| Full Scope (3 devs) |  | ~2.4 months (~9.8 wks) |

Both critical open questions (Q14 and Q28) resolved with 0 hours impact. Client chose the simplest design options in both cases — no reservation at bid stage, auto-release after partial allocation, Admin as single decision point at approval. These answers unblock ~222 hrs of combined estimation work (items #16, #22, #25, #26, #28, #34) and significantly reduce the 'Partial/split allocation business rules unclear' risk. Only Q29 (total user count / external access) remains as a critical open question. Timeline unchanged: MVP ~3.3 months (2 devs) or ~2.2 months (3 devs). Full scope ~3.7 months (2 devs) or ~2.4 months (3 devs).

# Cumulative Impact

| Cumulative Metric | Value |
| --- | --- |
| Total Change Batches | 1 |
| Total Individual Changes | 2 |
| Original MVP Estimate | ~998 hrs |
| Current MVP Estimate | ~998 hrs |
| Cumulative Net Impact on MVP | 0 hrs |
| Original Full Scope | ~1171 hrs |
| Current Full Scope | ~1171 hrs |
| Current MVP Timeline (2 devs) | ~3.3 months |
| Current MVP Timeline (3 devs) | ~2.2 months |

This document is updated each time client answers or stakeholder decisions affect the project scope. All changes reference the specific trigger (Q&A answer, meeting decision, or discovery finding) that justified the modification.