Estimation: Bid Intelligence Platform

ReMarkets — Bid Intelligence Platform

Option B — Blazor Web App + .NET 10

# Scope Summary

Internal web application for REMarkets to replace spreadsheet/email-based bidding workflows. Covers bid management, inventory handling, allocation approvals, role-based access, act-on-behalf, audit trails, and order-ready exports. Authentication via Microsoft Entra. All data stored in clean, normalized SQL for future analytics consumption.

# Architecture Summary

- Frontend + Backend: Blazor Web App (.NET 10) — unified C# codebase

- Render Modes: Static SSR for simple pages, Interactive Server for bid tables and allocation views

- UI Components: MudBlazor (free) with DataGrid for in-cell editing

- Database: Azure SQL Database with Entity Framework Core 10 (Code-First)

- Auth: Microsoft Entra ID via Microsoft.Identity.Web (built-in Blazor auth)

- Hosting: Azure App Service (3 environments: Dev, Test, Prod)

- Deploy: Single project, single deploy

# Data Grid Library Options

The in-cell editing grid is the most critical UI component — it’s where sales reps enter bids, quantities, and prices directly in a table (like Excel in the browser).

| Library | License | Cost | In-Cell Editing | Notes |
| --- | --- | --- | --- | --- |
| MudBlazor DataGrid (Recommended) | MIT (free, open source) | $0 | Good | Active community, evaluate Sprint 0 |
| Radzen DataGrid | MIT (free, open source) | $0 | Good | Alternative to MudBlazor |
| AG Grid (Blazor wrapper) | Community: MIT / Enterprise: Commercial | ~$1,100/dev | Best-in-class | Same AG Grid as React |
| Telerik UI for Blazor | Commercial (paid license) | ~$1,000/dev/yr | Excellent | Full UI suite + professional support |
| Syncfusion Blazor | Community: free <$1M rev | $0 or ~$995/dev/yr | Very good | Free tier may apply |
| Manual (jQuery/JS) | N/A | $0 | Painful | NOT recommended — conflicts with Blazor DOM |

Recommendation: Start with MudBlazor (free, MIT). If Sprint 0 shows it’s insufficient, upgrade to Telerik or AG Grid (~$2–3K for 2–3 devs).

# MVP Definition

Core question: Can REMarkets run 100% of internal bid-to-allocation workflows through the platform instead of spreadsheets and email?

MVP goal: A working web application where sales reps can create offers, enter bids, upload inventory, and route allocations through an approval workflow — with full audit logging and role-based access.

# MVP Scope (Must Have)

Without these, the project fails to replace the current spreadsheet/email process.

| # | Module | Task | Complexity | Base Hrs | Factor | Adjusted | Notes |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Project Setup |  |  |  |  |  |  |  |
| 1 | Setup | Blazor Web App project scaffolding (Clean Architecture) | Low | 12 | ×1.2 | 14 | Single project, C# only |
| 2 | Setup | EF Core setup, initial migrations, seed data | Low | 12 | ×1.2 | 14 |  |
| 3 | Setup | CI/CD pipeline (build + test + deploy) | Low | 10 | ×1.2 | 12 | Single project = simpler pipeline |
| Authentication & Authorization — Option A: Azure AD Groups (Confirmed) |  |  |  |  |  |  |  |
| 4 | Auth | Entra integration — Microsoft.Identity.Web (built-in Blazor auth) | Medium | 12 | ×1.5 | 18 | Simpler than MSAL.js |
| 5 | Auth | Azure AD Group setup + group claims mapping (5 groups) | Medium | 10 | ×1.5 | 15 | Configure groups in Azure AD |
| 6 | Auth | Dynamic role-based authorization + app-layer enforcement | Medium | 14 | ×1.5 | 21 | Policies reading AD group claims |
| 7 | Auth | AuthorizeView components (dynamic role-based UI rendering) | Low | 12 | ×1.2 | 14 | Show/hide based on group membership |
| Customer Management |  |  |  |  |  |  |  |
| 8 | Customers | Customer CRUD (API + Blazor pages) | Low | 14 | ×1.2 | 17 | Standard CRUD |
| 9 | Customers | Customer assignment to Sales Reps/Managers | Low | 8 | ×1.2 | 10 |  |
| 10 | Customers | Customer deactivation (soft delete) + audit logging | Low | 8 | ×1.2 | 10 |  |
| Inventory Management |  |  |  |  |  |  |  |
| 11 | Inventory | Bulk CSV/Excel upload (parsing + validation + error handling) | High | 24 | ×2.0 | 48 | File parsing edge cases |
| 12 | Inventory | Inventory identity — composite uniqueness + master vs source description | High | 20 | ×2.0 | 40 | Client-confirmed composite key |
| 12b | Inventory | Master description edit UI (search + inline edit + role restriction) | Low | 6 | ×1.2 | 8 | SC-002 A15: dedicated UI, audited |
| 13 | Inventory | Inventory adjustment records (each upload = distinct transaction) | Medium | 14 | ×1.5 | 21 | Full audit trail per upload row |
| 14 | Inventory | Inventory list view with state tracking (Available/Committed/Released) | Medium | 14 | ×1.5 | 21 |  |
| 15 | Inventory | Inventory grouping into offers | Medium | 12 | ×1.5 | 18 |  |
| 16 | Inventory | State transitions (automatic on approval + manual override) | Medium | 16 | ×1.5 | 24 | Business rules complexity |
| Bid & Offer Management |  |  |  |  |  |  |  |
| 17 | Bids | Create/Edit offers (Blazor forms) | Medium | 14 | ×1.5 | 21 |  |
| 18 | Bids | Offer list view with filtering and sorting | Medium | 10 | ×1.5 | 15 |  |
| 19 | Bids | MudBlazor DataGrid — in-cell editing for line-item bids | High | 28 | ×2.0 | 56 | Core feature, DataGrid config |
| 20 | Bids | Bid uniqueness enforcement + revision tracking | Medium | 10 | ×1.5 | 15 | One active bid per customer/line/offer |
| 21 | Bids | Bid types support (bid/BIN/target pricing) | Medium | 12 | ×1.5 | 18 |  |
| 22 | Bids | Winning/losing bid capture and status tracking | Medium | 12 | ×1.5 | 18 |  |
| 23 | Bids | Bid history (view previous revisions per line item) | Medium | 14 | ×1.5 | 21 |  |
| Allocation & Approval Workflow |  |  |  |  |  |  |  |
| 24 | Allocation | Aggregated allocation view (all bids per offer) | Medium | 14 | ×1.5 | 21 |  |
| 25 | Allocation | Admin override of winning customer | Medium | 12 | ×1.5 | 18 |  |
| 26 | Allocation | Approval workflow (Pending → Approved/Rejected) — all manager-approved Phase 1 | High | 24 | ×2.0 | 48 | Admin has full authority incl. override |
| 27 | Allocation | Visual pricing indicators (“below floor” warnings) | Medium | 8 | ×1.5 | 12 | Visual only Phase 1, no auto-reject |
| 28 | Allocation | Automatic inventory commitment on approval | Medium | 12 | ×1.5 | 18 |  |
| Allocation Reversal (Client-confirmed) |  |  |  |  |  |  |  |
| 29 | Allocation | Allocation reversal (return inv. to Available, mark Reversed, lock export) | High | 20 | ×2.0 | 40 | State machine + inventory rollback |
| 30 | Allocation | Reversal reason code (required) + full audit trail | Medium | 8 | ×1.5 | 12 | Reason code dropdown + audit |
| Allocation Tie-Breaker (Client-confirmed) |  |  |  |  |  |  |  |
| 31 | Allocation | Tie detection logic + resolution UI | Medium | 8 | ×1.5 | 12 | Admin picks winner from tied bids |
| Act-on-Behalf (Client-requested — Kim: “very important”) |  |  |  |  |  |  |  |
| 32 | Act-on-Behalf | Act-on-behalf capability — full attribution + audit | High | 24 | ×2.0 | 48 | Custom AuthenticationStateProvider |
| 33 | Act-on-Behalf | Act-on-behalf UI (customer selector + visual indicator) | Medium | 10 | ×1.5 | 15 | Clear visual cue |
| Split Allocations (Client-requested) |  |  |  |  |  |  |  |
| 34 | Allocation | Partial/split allocations across customers | High | 24 | ×2.0 | 48 | Manual decision by manager |
| Audit & Compliance |  |  |  |  |  |  |  |
| 35 | Audit | Audit logging middleware (insert-only AuditLog table) | Medium | 16 | ×1.5 | 24 |  |
| 36 | Audit | Audit trail UI (view history per entity) | Medium | 14 | ×1.5 | 21 |  |
| Order-Ready Exports |  |  |  |  |  |  |  |
| 37 | Exports | CSV export from approved allocations | Low | 8 | ×1.2 | 10 |  |
| Permissions UI |  |  |  |  |  |  |  |
| 38 | Permissions | Role-based UI visibility (AuthorizeView across pages) | Medium | 14 | ×1.5 | 21 |  |
| Testing & Bug Buffer |  |  |  |  |  |  |  |
| 39 | QA | Unit tests (services + critical business logic) | Medium | 20 | ×1.5 | 30 |  |
| 40 | QA | Integration tests (API/page endpoints) | Medium | 14 | ×1.5 | 21 |  |
| 41 | QA | Bug fixing buffer (10% of MVP hours) | — | — | — | 90 | Based on ~900 hrs pre-buffer |
| MVP Total (Auth Option A) |  |  |  |  |  | ~998 hrs |  |

# Post-MVP Scope (Should Have)

Features that add value after MVP is stable.

| # | Module | Task | Complexity | Base Hrs | Factor | Adjusted | Source |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 42 | Allocation | Escalation paths (auto-escalate if not approved in X time) | Medium | 16 | ×1.5 | 24 | Suggested enhancement |
| 43 | Exports | PDF export (order-ready documents via QuestPDF) | Medium | 14 | ×1.5 | 21 | Client mentioned; CSV is in MVP |
| 44 | Audit | Advanced audit views (filter by user, date, entity type) | Medium | 10 | ×1.5 | 15 | Suggested enhancement |
| 45 | Admin | System configuration UI (thresholds, settings) | Medium | 14 | ×1.5 | 21 | Suggested enhancement |
| 46 | QA | UAT support + bug fixes from user feedback | Medium | 24 | ×1.5 | 36 | Standard |
| Post-MVP Total |  |  |  |  |  | ~117 hrs |  |

# Backlog (Could Have)

| # | Task | Source |
| --- | --- | --- |
| 47 | Dashboard with key metrics (active offers, pending approvals, recent bids) | Suggested enhancement |
| 48 | Bulk bid operations (approve/reject multiple at once) | Suggested enhancement |
| 49 | Advanced search and filtering across all entities | Suggested enhancement |
| 50 | Email notifications on approval status changes | Suggested enhancement |
| 51 | Data export API for future external consumption | Suggested enhancement |
| 52 | User activity log (who logged in when) | Suggested enhancement |

## Out of Scope (Won’t Have)

- Customer-facing portal (future phase)

- In-app analytics dashboards (future consideration)

- Mobile application

- Integration with external ERP or order management systems

- Email/notifications

# Learning Curve Budget

| Technology | Who | Hours | Justification |
| --- | --- | --- | --- |
| Blazor component model + render modes | Dev 1 | 12 | Components, lifecycle, SSR vs Interactive |
| Blazor component model + render modes | Dev 2 | 12 | Same |
| MudBlazor (DataGrid + UI components) | Dev 1 | 8 | Grid API, cell editing, forms |
| MudBlazor (DataGrid + UI components) | Dev 2 | 6 | Support knowledge |
| Microsoft.Identity.Web (Blazor auth) | Dev 1 | 6 | Built-in auth patterns |
| Azure App Service + SQL (if new) | Both | 8 | Deployment, config |
| CI/CD pipeline setup | TBD | 4 | Single project = simpler |

Learning Curve Total: ~56 hrs

# Risk Assessment

| Risk | Probability | Impact | Hours at Risk | Mitigation |
| --- | --- | --- | --- | --- |
| MudBlazor DataGrid insufficient for in-cell editing | Medium | High | +16-24 hrs | Evaluate Sprint 0; Telerik/Syncfusion fallback |
| SignalR connection reliability | Low | Medium | +8-16 hrs | Built-in reconnection; test under real network |
| Blazor community smaller | Medium | Medium | +8-16 hrs | MudBlazor Discord, Microsoft docs |
| Partial/split allocation rules unclear | Low | High | +24-40 hrs | SC-003 resolved: auto-release, no reservation, flat records |
| Allocation reversal edge cases | Medium | High | +16-24 hrs | Define reversal rules with POs; test with real scenarios |
| Inventory composite uniqueness conflicts | Medium | Medium | +8-16 hrs | Define exact rules with client; validate Sprint 0 |
| CSV upload edge cases | Medium | Medium | +8-16 hrs | Define validation rules; limit file sizes |
| Azure infra not available on time | Medium | High | Blocks 1-2 wk | Confirm access before Sprint 1 |
| Scope creep from 3 Product Owners | Medium | High | +40-80 hrs | Reference charter; change request process |
| Open discovery questions (21 unresolved) | High | High | +40-150 hrs | Prioritize before Sprint 1; see discovery-questions.md |

# Summary

| Concept | Hours |
| --- | --- |
| MVP (Must Have) — Auth Option A: Azure AD Groups | ~998 hrs |
| MVP (Must Have) — Auth Option B: Internal DB Roles | ~1,022 hrs |
| Post-MVP (Should Have) | ~117 hrs |
| Learning Curve | ~56 hrs |
| Full Scope (MVP + Post-MVP + Learning) — Auth Option A | ~1,171 hrs |
| Full Scope (MVP + Post-MVP + Learning) — Auth Option B | ~1,195 hrs |

Updated Feb–Mar 2026 after client Q&A. SC-001: +146 hrs. SC-002: +8 hrs. SC-003: 0 hrs (design decisions only, no new scope).

## Timeline Scenarios — Auth Option A (2 developers, 80 hrs/week)

| Scenario | Scope | Hours | Calendar Estimate |
| --- | --- | --- | --- |
| MVP only | Must Have + Learning | ~1054 hrs | ~13.2 weeks (~3.3 months) |
| MVP + Post-MVP | Full Phase 1 | ~1,171 hrs | ~14.6 weeks (~3.7 months) |

## With 3 developers (120 hrs/week)

| Scenario | Scope | Hours | Calendar Estimate |
| --- | --- | --- | --- |
| MVP only | Must Have + Learning | ~1054 hrs | ~8.8 weeks (~2.2 months) |
| MVP + Post-MVP | Full Phase 1 | ~1,171 hrs | ~9.8 weeks (~2.4 months) |

Auth Option B adds ~24 hrs to all scenarios. Timelines assume devs are productive from week 1 after learning curve. Actual ramp-up may add 1–2 weeks.

# Head-to-Head: React vs Blazor

| Metric | React + .NET 10 | Blazor + .NET 10 | Difference |
| --- | --- | --- | --- |
| MVP Hours (Auth Option A) | ~1,100 hrs* | ~998 hrs | Blazor saves ~102 hrs |
| Post-MVP Hours | ~126 hrs | ~117 hrs | Blazor saves ~9 hrs |
| Learning Curve | ~100 hrs | ~56 hrs | Blazor saves ~44 hrs |
| Total Hours (Auth Option A) | ~1,326 hrs* | ~1,171 hrs | Blazor saves ~155 hrs |
| MVP Timeline (2 devs) | ~15 weeks* | ~13.2 weeks | ~1.8 weeks faster |
| Full Scope Timeline (2 devs) | ~16.5 weeks* | ~14.6 weeks | ~1.9 weeks faster |
| In-cell editing quality | Best (AG Grid) | Good (MudBlazor) | React has better grid |
| Future customer portal | Excellent | Good | React better long-term |
| Hiring future devs | Excellent | Limited | React market larger |
| CI/CD complexity | Medium (2 deploys) | Low (1 deploy) | Blazor simpler |

* React estimation not yet updated with client Q&A scope changes. Numbers are projected proportional estimates.

Bottom line: Blazor saves ~160 hours and ~2 weeks on timeline. React costs more upfront but offers better in-cell editing, easier hiring, and a stronger path to a future customer portal.

# Team Sign-off

| Name | Role | Approved |
| --- | --- | --- |
| TBD | Simpat Lead |  |
| TBD | Dev 1 |  |
| TBD | Dev 2 |  |