Estimation: Bid Intelligence Platform

EMPA-ReMarkets — Bid Intelligence Platform — Blazor Web App + .NET 10

# Scope Summary

Internal web application for REMarkets to replace spreadsheet/email-based bidding workflows. Covers bid management, inventory handling, allocation approvals, role-based access, act-on-behalf, audit trails, and order-ready exports. Authentication via Microsoft Entra. All data stored in clean, normalized SQL for future analytics consumption.

# Architecture Summary

- Frontend + Backend: Blazor Web App (.NET 10) — unified C# codebase

- Render Modes: Static SSR for simple pages, Interactive Server for bid tables and allocation views

- UI Components: MudBlazor (free) with DataGrid for in-cell editing

- Database: Azure SQL Database with Entity Framework Core 10 (Code-First)

- Auth: Microsoft Entra ID via Microsoft.Identity.Web (built-in Blazor auth)

- Hosting: Azure App Service (3 environments: Dev, Test, Prod — TBD if already provisioned)

- Deploy: Single project, single deploy

# Data Grid Library Options (In-Cell Editing — Core Feature)

The in-cell editing grid is the most critical UI component — it’s where sales reps enter bids, quantities, and prices directly in a table (like Excel in the browser). Without this, every edit requires opening a separate form per line item.

| Library | License | Cost | In-Cell Editing | Notes |
| --- | --- | --- | --- | --- |
| MudBlazor DataGrid ★ Recommended | MIT (free, open source) | $0 | ★★★★ Good | Active community, good docs, evaluate in Sprint 0 |
| Radzen DataGrid | MIT (free, open source) | $0 | ★★★★ Similar | Alternative if MudBlazor doesn't fit |
| AG Grid (Blazor wrapper) | Community: MIT / Enterprise: Commercial | ~$1,100/dev | ★★★★★ Best-in-class | Same AG Grid as React, has Blazor wrapper |
| Telerik UI for Blazor | Commercial (paid license) | ~$1,000/dev/yr | ★★★★★ Excellent | Full UI suite with professional support |
| Syncfusion Blazor | Community: free <$1M / Commercial | $0 or ~$995/dev/yr | ★★★★ Very good | Free tier may apply |
| Manual (jQuery/JS) | N/A | $0 | ★★ Painful | Not recommended — conflicts with Blazor DOM |

Recommendation: Start with MudBlazor (free, MIT). If during Sprint 0 the DataGrid doesn’t handle the in-cell editing complexity needed, upgrade to Telerik or AG Grid (~$2-3K for 2-3 devs).

Why not build it manually? Blazor controls the entire page DOM through C#. Adding jQuery or raw JavaScript creates two systems fighting over the same page elements — guaranteed bugs.

# MVP Definition

Core question: Can REMarkets run 100% of internal bid-to-allocation workflows through the platform instead of spreadsheets and email?

MVP goal: A working web application where sales reps can create offers, enter bids, upload inventory, and route allocations through an approval workflow — with full audit logging and role-based access.

## MVP Scope (Must Have)

Without these, the project fails to replace the current spreadsheet/email process.

| # | Module | Task | Complexity | Base Hrs |  | Factor | Adjusted | Notes |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Project Setup |  |  |  |  |  |  |  |  |
| 1 | Setup | Blazor Web App project scaffolding (Clean Architecture) | Low | 12 | ×1.2 |  | 14 | Single project, C# only |
| 2 | Setup | EF Core setup, initial migrations, seed data | Low | 12 | ×1.2 |  | 14 |  |
| 3 | Setup | CI/CD pipeline (build + test + deploy) | Low | 10 | ×1.2 |  | 12 | Single project = simpler pipeline |
| Authentication & Authorization |  |  |  |  |  |  |  |  |
| Option A: Azure AD Groups (Confirmed) — Roles managed in Azure AD — no user/role tables in app DB |  |  |  |  |  |  |  |  |
| 4 | Auth | Entra integration — Microsoft.Identity.Web (built-in Blazor auth) | Medium | 12 | ×1.5 |  | 18 | Simpler than MSAL.js — built-in support |
| 5 | Auth | Azure AD Group setup + group claims mapping (5 groups: Sales Rep, Sales Manager, Admin, Finance, Executive) | Medium | 10 | ×1.5 |  | 15 | Configure groups in Azure AD, map to app roles via token claims |
| 6 | Auth | Dynamic role-based authorization (policies reading AD group claims) + app-layer enforcement | Medium | 14 | ×1.5 |  | 21 | API and services enforce roles from AD groups; app-layer enforcement required per client |
| 7 | Auth | AuthorizeView components (dynamic role-based UI rendering from AD claims) | Low | 12 | ×1.2 |  | 14 | Show/hide/disable UI elements based on group membership |
| Auth Option A subtotal — 68 hrs |  |  |  |  |  |  |  |  |
| Customer Management |  |  |  |  |  |  |  |  |
| 8 | Customers | Customer CRUD (API + Blazor pages) | Low | 14 | ×1.2 |  | 17 | Standard CRUD |
| 9 | Customers | Customer assignment to Sales Reps/Managers | Low | 8 | ×1.2 |  | 10 |  |
| 10 | Customers | Customer deactivation (soft delete) + audit logging | Low | 8 | ×1.2 |  | 10 |  |
| Inventory Management |  |  |  |  |  |  |  |  |
| 11 | Inventory | Bulk CSV/Excel upload (parsing + validation + error handling) | High | 24 | ×2.0 |  | 48 | File parsing edge cases |
| 12 | Inventory | Inventory identity — composite uniqueness (PartNumber + condition + location + grade) + master vs source description logic | High | 20 | ×2.0 |  | 40 | Client-confirmed: net-new → populate master; existing → retain source only; master changes require Admin/Manager action |
| 13 | Inventory | Inventory adjustment records (each upload row = distinct transaction: batch ID, user, timestamp, qty, source file) | Medium | 14 | ×1.5 |  | 21 | Client-confirmed: never silently merge — full audit trail per upload row |
| 14 | Inventory | Inventory list view with state tracking (Available/Committed/Released) | Medium | 14 | ×1.5 |  | 21 |  |
| 15 | Inventory | Inventory grouping into offers | Medium | 12 | ×1.5 |  | 18 |  |
| 16 | Inventory | State transitions (automatic on approval + manual override) | Medium | 16 | ×1.5 |  | 24 | Business rules complexity |
| Bid & Offer Management |  |  |  |  |  |  |  |  |
| 17 | Bids | Create/Edit offers (Blazor forms) | Medium | 14 | ×1.5 |  | 21 |  |
| 18 | Bids | Offer list view with filtering and sorting | Medium | 10 | ×1.5 |  | 15 |  |
| 19 | Bids | MudBlazor DataGrid — in-cell editing for line-item bids | High | 28 | ×2.0 |  | 56 | Core feature, DataGrid config |
| 20 | Bids | Bid uniqueness enforcement (one active bid per customer per line per offer) + revision tracking | Medium | 10 | ×1.5 |  | 15 | Client-confirmed: new revision on update, previous retained for audit, only latest active |
| 21 | Bids | Bid types support (bid/BIN/target pricing) | Medium | 12 | ×1.5 |  | 18 |  |
| 22 | Bids | Winning/losing bid capture and status tracking | Medium | 12 | ×1.5 |  | 18 |  |
| 23 | Bids | Bid history (view previous revisions per line item) | Medium | 14 | ×1.5 |  | 21 |  |
| Allocation & Approval Workflow |  |  |  |  |  |  |  |  |
| 24 | Allocation | Aggregated allocation view (all bids per offer) | Medium | 14 | ×1.5 |  | 21 |  |
| 25 | Allocation | Admin override of winning customer | Medium | 12 | ×1.5 |  | 18 |  |
| 26 | Allocation | Approval workflow (Pending → Approved/Rejected) — all manager-approved in Phase 1 | High | 24 | ×2.0 |  | 48 | Client-confirmed: thresholds out of scope Phase 1; Admin has full authority including override |
| 27 | Allocation | Visual pricing indicators ("below floor" warnings) — thresholds configurable in future phase | Medium | 8 | ×1.5 |  | 12 | Client-confirmed: visual only in Phase 1, no auto-reject |
| 28 | Allocation | Automatic inventory commitment on approval | Medium | 12 | ×1.5 |  | 18 |  |
| Allocation Reversal — Client-confirmed — must support in Phase 1 |  |  |  |  |  |  |  |  |
| 29 | Allocation | Allocation reversal (return inventory to Available, mark as Reversed, lock/regenerate export) | High | 20 | ×2.0 |  | 40 | State machine change + inventory rollback + export invalidation |
| 30 | Allocation | Reversal reason code (required) + full audit trail for reversals | Medium | 8 | ×1.5 |  | 12 | Reason code dropdown + audit entry |
| Allocation Tie-Breaker — Client-confirmed — system surfaces ties, manager resolves manually |  |  |  |  |  |  |  |  |
| 31 | Allocation | Tie detection logic + resolution UI (surface tied bids, force manual winner selection) | Medium | 8 | ×1.5 |  | 12 | Admin/Manager picks winner from tied bids |
| Act-on-Behalf (Sales enters bids for customers) — Client-requested — needed from day 1 |  |  |  |  |  |  |  |  |
| 32 | Act-on-Behalf | Act-on-behalf capability — sales rep enters bids on behalf of a customer with full attribution | High | 24 | ×2.0 |  | 48 | Custom AuthenticationStateProvider; tracks who acted + for whom |
| 33 | Act-on-Behalf | Act-on-behalf UI (customer selector + visual indicator showing active customer context) | Medium | 10 | ×1.5 |  | 15 | Clear visual cue that rep is acting for customer |
| Split Allocations — Client-requested |  |  |  |  |  |  |  |  |
| 34 | Allocation | Partial/split allocations across customers (divide quantity of a line item between multiple winners) | High | 24 | ×2.0 |  | 48 | Manual decision by manager, not automated |
| Audit & Compliance |  |  |  |  |  |  |  |  |
| 35 | Audit | Audit logging middleware (insert-only AuditLog table) | Medium | 16 | ×1.5 |  | 24 |  |
| 36 | Audit | Audit trail UI (view history per entity) | Medium | 14 | ×1.5 |  | 21 |  |
| Order-Ready Exports |  |  |  |  |  |  |  |  |
| 37 | Exports | CSV export from approved allocations | Low | 8 | ×1.2 |  | 10 |  |
| Permissions UI |  |  |  |  |  |  |  |  |
| 38 | Permissions | Role-based UI visibility (AuthorizeView across pages) | Medium | 14 | ×1.5 |  | 21 |  |
| Testing & Bug Buffer |  |  |  |  |  |  |  |  |
| 39 | QA | Unit tests (services + critical business logic) | Medium | 20 | ×1.5 |  | 30 |  |
| 40 | QA | Integration tests (API/page endpoints) | Medium | 14 | ×1.5 |  | 21 |  |
| 41 | QA | Bug fixing buffer (10% of MVP hours) | — | — | — |  | 90 | Based on ~900 hrs pre-buffer |
| MVP Total (Auth Option A) |  |  |  |  |  |  | ~990 hrs |  |

## Post-MVP Scope (Should Have)

Features that add value after MVP is stable.

| # | Module | Task | Complexity | Base Hrs | Factor | Adjusted | Source |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 42 | Allocation | Escalation paths (auto-escalate if not approved in X time) | Medium | 16 | ×1.5 | 24 | Suggested enhancement |
| 43 | Exports | PDF export (order-ready documents via QuestPDF) | Medium | 14 | ×1.5 | 21 | Client mentioned "order-ready exports" — CSV is in MVP, PDF is extra |
| 44 | Audit | Advanced audit views (filter by user, date, entity type) | Medium | 10 | ×1.5 | 15 | Suggested enhancement |
| 45 | Admin | System configuration UI (thresholds, settings — avoid hardcoding) | Medium | 14 | ×1.5 | 21 | Suggested enhancement |
| 46 | QA | UAT support + bug fixes from user feedback | Medium | 24 | ×1.5 | 36 | Standard |
| Post-MVP Total |  |  |  |  |  | ~117 hrs |  |

## Backlog (Could Have)

| # | Task | Source |
| --- | --- | --- |
| 47 | Dashboard with key metrics (active offers, pending approvals, recent bids) | Suggested enhancement |
| 48 | Bulk bid operations (approve/reject multiple at once) | Suggested enhancement |
| 49 | Advanced search and filtering across all entities | Suggested enhancement |
| 50 | Email notifications on approval status changes | Suggested enhancement |
| 51 | Data export API for future external consumption | Suggested enhancement |
| 52 | User activity log (who logged in when) | Suggested enhancement |

## Out of Scope (Won’t Have)

- Customer-facing portal (future phase)

- In-app analytics dashboards (future consideration)

- Commodities pricing database / AI training data

- Mobile application

- Integration with external ERP or order management systems

# Learning Curve Budget

| Technology | Who | Hours | Justification |
| --- | --- | --- | --- |
| Blazor component model + render modes | Dev 1 | 12 | Components, lifecycle, SSR vs Interactive |
| Blazor component model + render modes | Dev 2 | 12 | Same |
| MudBlazor (DataGrid + UI components) | Dev 1 | 8 | Grid API, cell editing, forms |
| MudBlazor (DataGrid + UI components) | Dev 2 | 6 | Support knowledge |
| Microsoft.Identity.Web (Blazor auth) | Dev 1 | 6 | Built-in auth patterns |
| Azure App Service + SQL (if new) | Both | 8 | Deployment, connection strings, config |
| CI/CD pipeline setup | TBD | 4 | Single project = simpler |
| Learning Curve Total |  | 56 hrs |  |

# Summary

| Concept | Hours |
| --- | --- |
| MVP (Must Have) — Auth Option A: Azure AD Groups | ~990 hrs |
| Post-MVP (Should Have) | ~117 hrs |
| Learning Curve | ~56 hrs |
| Full Scope (MVP + Post-MVP + Learning) | ~1,163 hrs |

Updated Feb 2026 after client Q&A. Items added: inventory identity/dedupe (+61 hrs), bid uniqueness (+15 hrs), allocation reversal (+52 hrs), tie-breaker (+12 hrs), below floor indicator (+12 hrs). Thresholds simplified (-9 hrs). 27 discovery questions still open.

## Timeline Scenarios — Auth Option A (2 developers, 80 hrs/week)

| Scenario | Scope | Hours | Working Weeks | Calendar |
| --- | --- | --- | --- | --- |
| MVP only | Must Have + Learning | ~1,046 hrs | ~13 weeks | ~3.25 months |
| MVP + Post-MVP | Full Phase 1 | ~1,163 hrs | ~14.5 weeks | ~3.6 months |

## With 3 developers (120 hrs/week)

| Scenario | Scope | Hours | Working Weeks | Calendar |
| --- | --- | --- | --- | --- |
| MVP only | Must Have + Learning | ~1,046 hrs | ~8.5 weeks | ~2.1 months |
| MVP + Post-MVP | Full Phase 1 | ~1,163 hrs | ~9.7 weeks | ~2.4 months |

Auth Option B adds ~24 hrs. Timelines assume productive from week 1 after learning curve. Ramp-up may add 1-2 weeks. Does not include UAT.

# Risk Assessment

| Risk | Probability | Impact | Hours at Risk | Mitigation |
| --- | --- | --- | --- | --- |
| MudBlazor DataGrid insufficient for in-cell editing | Medium | High | +16-24 hrs + $1K/dev | Evaluate in Sprint 0; Telerik/Syncfusion as fallback |
| SignalR connection reliability | Low | Medium | +8-16 hrs | Built-in reconnection; test under real network |
| Blazor community smaller — harder to find solutions | Medium | Medium | +8-16 hrs per incident | MudBlazor Discord, Microsoft docs |
| Partial/split allocation business rules unclear | High | High | +24-40 hrs | Define rules with Product Owners before coding |
| Allocation reversal edge cases (partial reversals, already-exported data) | Medium | High | +16-24 hrs | Define reversal rules explicitly with POs; test with real scenarios |
| Inventory composite uniqueness conflicts | Medium | Medium | +8-16 hrs | Define exact uniqueness rules with client; validate during Sprint 0 |
| CSV upload edge cases (bad data, large files) | Medium | Medium | +8-16 hrs | Define validation rules upfront; limit file sizes |
| Azure infra not available on time | Medium | High | Blocks 1-2 weeks | Confirm access before Sprint 1 |
| Scope creep from 3 Product Owners | Medium | High | +40-80 hrs | Reference charter; change request process |

# TBD Impact on Estimation

| Unknown | If Confirmed As... | Impact on Hours |
| --- | --- | --- |
| Auth approach: Azure AD vs Internal DB | Option A: Azure AD Groups (recommended) | Auth = 68 hrs (baseline) |
| Auth approach: Azure AD vs Internal DB | Option B: Internal DB roles + admin UI | Auth = 92 hrs (+24 hrs) |
| 3rd developer available | Yes | Timeline compresses ~30% |
| 3rd developer available | No | Stays at 2-dev scenario |
| MudBlazor DataGrid sufficient | No — need Telerik/Syncfusion | +$1-2K license, +8-16 hrs |
| Automated infrastructure setup | Yes | +16-24 hrs |

# Team Sign-off

| Name | Role | Approved |
| --- | --- | --- |
| TBD | Simpat Lead |  |
| TBD | Dev 1 |  |
| TBD | Dev 2 |  |